## PO
Test Nature | Test cases | Expected | Actual | Remarks |  | 20160314 | 20160324 | 20160406
File name and structure | Name file as MS002_POR_20151231 | Integration not triggered because POR is not valid
| Name file as MS003_PO_20151231 | Integration not triggered. System only detects PO, regardless the first prefix is MS002 or MS003
| missing one column cln_code | Integration throws error
| add one column in excel file | Integration throws error
Data | For customer type FFS (not capitation)
| To accrue cost for customer type FFS | One journal is created per clinic code, incurred month and type (FFS/CAP) |  | One clinic may have different customers. Some customers in FFS while some customers in CAP. Two journal should be created, one for FFS, one for CAP |  | Journal entry get overwritten, refer to diagram below | journal entry is still overwritten, refer to second diagram below. | fine
|  | journal posting date is incurred month |  |  |  | Fine
|  | Journal remarks is "Estimated cost for <ap code>" |  |  |  | Fine
|  | journal GL account DR FFS Panel Provider (cmoney) CR Admin Fee (oper) CR Fee For Services (pay_client) CR Accrued COGS |  | amount should be split for different MBMS |  | Fine
|  | GL accounts are split for each MBMS. Each MBMS should have three GL accounts. Check the amount is correct for each MBMS |  |  |  | Cost center change to upper case in both excel and sap | When retrieve cost center from sap, convert mbms table cost center and sap cost center setup to uppercase to match If mbms cost center is OTHERS, sap cost center setup is Others. Error "Link value "OTHERS" does not exist | fine
For customer type Capitation
| To accrue cost for customer type Capitation | One journal is created per clinic code, incurred month and type (FFS/CAP) |  | One clinic may have different customers. Some customers in FFS while some customers in CAP. Two journal should be created in this case | Fine | Fine
|  | journal posting date is incurred month |  |  | Fine | Fine
|  | Journal remarks is "Estimated cost for <ap code>" |  |  | Fine | Fine
|  | journal GL account DR CAP - Panel Provider Fee (cmoney - pay_client) DR FFS Panel Provider (pay_client) CR Fee For Services (pay_client) CR Admin Fee (Oper) Cr Accrued COGS |  | amount should be split for different MBMS | Fine | Fine
|  | GL accounts are split for each MBMS. Each MBMS should have four GL accounts. Check the amount is correct for each MBMS |  |  | Fine | Cost center change to upper case in both excel and sap | When retrieve cost center from sap, convert mbms table cost center and sap cost center setup to uppercase to match If mbms cost center is OTHERS, sap cost center setup is Others. Error "Link value "OTHERS" does not exist | fine
Validation Check | Duplicate invoice number is uploaded after it is processed and accrual journal was created in SAP in previous files | Throw error and tell row number in log file |  |  |  | No error prompted | Fine
| company code not found in SAP | Throw error and tell row number in log file
| AP code not found in SAP | Throw error and tell row number in log file
| scheme code is null in the source file | Throw error and tell row number in log file
| Duplicate MBMS found for same customer in same period and scheme code | Throw error and tell row number in log file
| MBMS nof found, for eg scheme code does not match, effective date is not valid | Throw error and tell row number in log file
MBMS Check | Refer to "MBMS" sheet
Validation Check
HMDC

## AP
Test Nature | Test cases | Expected | Actual | Remarks | 20160324 | 20160406
File name and structure | Name file as MS002_APR_20151231 | Integration not triggered because APR is not valid
| Name file as MS003_AP_20151231 | Integration not triggered. System only detects AP, regardless the first prefix is MS002 or MS003
| missing one column cln_code | Testing has been done in PO
| add one column in excel file | Testing has been done in PO
Data | For customer type FFS (not capitation)
| To create AP invoice for customer type FFS | One AP invoice is created per clinic code, incurred month and type (FFS/CAP) |  | One clinic may have different customers. Some customers in FFS while some customers in CAP. Two invoices should be created, one for FFS, one for CAP |  | Currently the invoice will be split if it is different MBMS (based on company code). It should be in same invoice with different MBMS at line level for the same clinic
|  | invoice posting date is the date in the upload file name |  |  | It is today's date | It is today's date
|  | invoice ap code = V + clinic code + subcode |  |  | Fine
|  | Item code in the invoice lines FFS Panel Provider - cmoney Admin Fee - oper (negative amount) Fee For Services - pay_client (negative amount) |  | amount should be split for different MBMS | admin fee and fee for service is not negative | Fine
|  | Check journal entry for the invoice DR FFS Panel Provider (cmoney) CR Admin Fee (oper) CR Fee For Services (pay_client) CR AP |  |  | wrong because of admin and ffs not negative | Fine
Each MBMS has three item lines. Check the amount is correct for each MBMS
|  | Cost accrual journal is reversed per clinic code, incurred month and type (FFS/CAP) |  |  | No reversal entry should be made if the invoice cannot be found in COSTACCRUAL table | Reversal entry is not made even the invoice can be found in costaccrual table. Refer to AP Reversal worksheet
|  | journal remarks is "Reversal of Estimated cost for <clinic code>" |  |  |  | the remarks now is "Reversal of Estimated Sales for <customer code>"
|  | Reversal journal posting date is the date in the upload file name |  |  |  | Fine
|  | Reversal journal GL accounts CR FFS Panel Provider (cmoney) DR Admin Fee (oper) DR Fee For Services (pay_client) DR Accrued COGS |  |  |  | Fine
|  | Reversal amount should follow the invoice amount uploaded in PO file, not AP |  |  |  | Currently it is based on AP file amount
|  | GL accounts are split for each MBMS. Each MBMS should have three GL accounts. Check the amount is correct for each MBMS |  |  | When retrieve cost center from sap, convert mbms table cost center and sap cost center setup to uppercase to match Refer to diagram below
For customer type Capitation
| To create AP invoice for customer type CAP | One AP invoice is created per clinic code, incurred month and type (FFS/CAP) |  | One clinic may have different customers. Some customers in FFS while some customers in CAP. Two invoices should be created, one for FFS, one for CAP | Currently the invoice will be split if it is different MBMS (based on company code). It should be in same invoice with different MBMS at line level | Fine
|  | invoice posting date is the date in the upload file name |  |  | Now is current date | It is today's date
|  | invoice ap code = V + clinic code + subcode |  |  | fine
|  | Item code in the invoice lines CAP - Panel Provider Fee - cmoney-pay_client FFS Panel Provider - pay_client Admin Fee - oper (negative amount) Fee For Services - pay_client (negative amount) |  | amount should be split for different MBMS | admin fee is not negative Fee for Service is not negative | FFS Panel Provider should be positive, Fee for service should be negative. Refer to AE_ITEMCODE worksheet, if it is credit, it will be negative
|  | Check journal entry for the invoice DR CAP - Panel Provider Fee (cmoney - pay_client) DR FFS Panel Provider (pay_client) CR Fee For Services (pay_client) CR Admin Fee (Oper) Cr AP |  |  | wrong because admin and ffs is not negative
|  | Each MBMS has four item lines. Check the amount is correct for each MBMS |  |  | currently different MBMS will be split to separate invoice. Should be in one invoice with different mbms at line level
|  | Cost accrual journal is reversed per clinic code, incurred month and type (FFS/CAP) |  |  | No reversal entry should be made if the invoice cannot be found in COSTACCRUAL table | Reversal entry is not made even the invoice can be found in costaccrual table. Refer to AP Reversal worksheet
|  | journal remarks is "Reversal of Estimated cost for <clinic code>" |  |  |  | the remarks now is "Reversal of Estimated Sales for <customer code>"
|  | Reversal journal posting date is the date in the upload file name |  |  |  | Fine
|  | Reversal journal GL accounts CR CAP - Panel Provider Fee (cmoney - pay_client) CR FFS Panel Provider (pay_client) DR Fee For Services (pay_client) DR Admin Fee (Oper) DR Accrued COGS |  |  |  | Fine
Reversal amount should follow the invoice amount uploaded in PO file, not AP
|  | GL accounts are split for each MBMS. Each MBMS should have four GL accounts. Check the amount is correct for each MBMS |  |  | When retrieve cost center from sap, convert mbms table cost center and sap cost center setup to uppercase to match Refer to diagram below | Currently it is based on AP file amount
|  | Check invoice number is filled in MS002_AP |  |  |  | Invoice number is not filled after AP invoice created, refer to Invoice_no workshet
Validation Check | Duplicate invoice number is uploaded after it is processed and invoice created in SAP in previous files | Throw error and tell row number in log file |  |  | Fine
| company code not found in SAP | Testing has been done in PO
| AP code not found in SAP | Testing has been done in PO
| scheme code is null in the source file | Testing has been done in PO
| Duplicate MBMS found for same customer in same period and scheme code | Testing has been done in PO
| MBMS nof found, for eg scheme code does not match, effective date is not valid | Testing has been done in PO
MBMS Check | Refer to "MBMS" sheet | Testing has been done in PO

## SO2
Test Nature | Test cases | Expected | Actual 20160407 | Remarks
File name and structure | Name file as MS007_SOR_20151231 | Integration not triggered because SOR is not valid
| Name file as MS008_SO_20151231 | Integration not triggered. System only detects SO, regardless the first prefix is MS007 or MS008
| missing one column cln_code | Integration throws error
| add one column in excel file | Integration throws error
Data | Clinic not TPA (@AE_TPA_APCODE)
For customer type FFS (not capitation)
| To accrue sales for FFS | One journal is created per company code, incurred month and MBMS | Fine
|  | journal posting date is incurred month | Fine
|  | Journal remarks is "Estimated sales for <ar code>" | Fine
|  | journal GL account DR Accrued Revenue CR Fee For Service (pay comp) | Fine
| For customer type Capitation | No accrual | Fine
Clinic is TPA (@AE_TPA_APCODE)
For customer type FFS (not capitation)
| To accrue reimbursement for TPA income | One journal is created per clinic code, incurred month and MBMS, Type (FFS/CAP) | Fine
|  | journal posting date is incurred month | Fine
|  | journal GL account Dr Accrued revenue CR TPA Income (pay comp) | Fine
|  | Journal remarks is "Estimated TPA Claim for <ap code>" | currently it is "Estimated cost for clinic V0010 and MBMS Others"
|  | One journal is created per clinic code, incurred month and MBMS, Type (FFS/CAP) | Fine
|  | journal posting date is incurred month | Fine
|  | Journal remarks is "Estimated TPA Reimbusement for <ap code>" | currently it is "Estimated cost for clinic V0010 and MBMS Others"
|  | journal GL account CR Accrued COGS (Panel) DR TPA INCOME (Pay comp) | Fine
| For customer type Capitation |  | There is error credit account cannot be empty but file is moved to success and data is created in MS002_SO and costaccrual table. JE not created
| To accrue cost for reimbursement to patient | One journal is created per clinic code, incurred month and MBMS, Type (FFS/CAP)
journal posting date is incurred month
Journal remarks is "Estimated cost for <ap code>"
journal GL account DR Reimbursement to patient (pay comp) CR Accrued COGS (Panel)
Validation Check | Duplicate invoice number is uploaded after it is processed and accrual journal was created in SAP in previous files | Throw error and tell row number in log file
| company code not found in SAP | Throw error and tell row number in log file
| AP code not found in SAP | Throw error and tell row number in log file
| scheme code is null in the source file | Throw error and tell row number in log file
| Duplicate MBMS found for same customer in same period and scheme code | Throw error and tell row number in log file
| MBMS nof found, for eg scheme code does not match, effective date is not valid | Throw error and tell row number in log file
MBMS Check | Refer to "MBMS" sheet
Validation Check
HMDC

## SO
No | Test cases | Expected | Actual | Remarks
1 | File name and file structure: Name file as MS007_SI_20151231 | Integration not triggered. Files will remain in INPUT | Fine
| Name file as MS008_SO_20151231 | Integration started | fine
| Name file as MS007_SO_20151231 | Integration started | fine
| missing one column cln_code | Integration throw erros "Length cannot be less than zero." | fine
| add one irrelevant column | integration throw error "Length cannot be less than zero." | fine
2 | Insurer and Cost Center Error: Create a scenario where the retrieval of insurer will return zero result. For eg: customer code cannot be found in @AE_MBMS | Throw error and stop processing "MBMS column cannot be null" | Fine
| scheme code is null in the source file | Throw error and stop processing "MBMS column cannot be null" | Fine
| Effective date in @AE_MBMS is greater than txn_date | Throw error and stop processing "MBMS column cannot be null" | Fine
| scheme code does not exist in @AE_MBMS | Throw error and stop processing "MBMS column cannot be null" | Fine
| Duplicate entry found for same period for same customer and scheme | Throw error "Duplicate insurer found" | Fine
| Please create another MBMS entry with earlier effective date. | should be able to retrieve the latest MBMS | if there is duplicate entry with different effective date, should not throw error duplicate MBMS, should be able to retrieve the current MBMS | Refer to duplicate MBMS and Sheet4
| Please create another MBMS entry with future effective date. | should be able to retrieve the current MBMS | Fine
3 | Assumption no data error: check backend UDT table has all the rows | All the content of the file should be inserted into UDT @AE_MS007_SO | Fine
| Check incurred month column in @AE_MS007_SO is last day of txn_date | If the txn_date in the file is 24102015, incurred month will be 31102015 | Fine
| check U_CostCenter and U_Insurer according to @AE_MBMS | insurer and MBMS returned will be according to the setup in @AE_MBMS | Fine
4 | Check data in @AE_SOACCRUAL: 1. check U_total_sales is summation of pay_comp amount group by company_code, incurred_month, and MBMS | sum pay_comp by company_code, incurred_month, and MBMS | Fine
5 | Check journal entry: check journal posting date | posting date = incurred_month | Fine
| check G/L accounts posted | As per @AE_MS007_GL | Fine
| check debit/credit amount | As per total_sales in @AE_SOACCRUAL | Fine
| check journal remarks | Remarks of the journal "JOURNAL ENTRY FOR COMPANY 1003" | Fine
| One journal is created per company code, incurred month and cost center | As per @AE_SOACCRUAL | Fine
6 | Check data in @AE_SOACCRUAL: check journal | journal entry number created for the sales accrual | Fine
7 | Repeat the steps 3- 6 for same company with different MBMS | two lines created in @AE_SOACCRUAL, two journal entries created | Fine
8 | Repeat the steps 3 - 6 for company type capitation | Data added to @AE_MS007_SO, No journal entry creation, no data added to @AE_SOACCRUAL | journal entry is created, data added in @AE_SOACCRUAL, Refer to "Capitation"
9 | Duplicate invoice: Repeat the step 3-6 with invoice number which has been closed before | throw error. Need to handle manually
10 | Check OUT network: Check if data exist in @AE_COSTACCRUAL | contains data which clinic code starts with "OUT" | Fine
| Check the pay_comp column in @AE_COSTACCRUAL | pay_comp should be summed for the same voucher | Fine
| check journal entry is posted to accrue cost | journal entry is created per clinic code and incurred month | Fine
| check journal posting date | posting date = incurred_month | Fine
| check G/L accounts posted | As per @AE_OUT_REV_GL | Fine
| check debit/credit amount | As per @AE_COSTACCRUAL | Fine
| check one journal is created per clinic code, incurred month and MBMS |  | Fine
| Check data in @AE_COSTACCRUAL: check journal | journal entry number created for the cost accrual | Fine
| Check data in @AE_SOACCRUAL: check journal | Not created | Fine
| Duplicate invoice for OUT in SO file after same invoice is closed | Throw error

## AR 2
Test Nature | Test cases | Expected | Actual 20160407 | Remarks
Data | Clinic not TPA (@AE_TPA_APCODE)
For customer type FFS (not capitation)
One ar invoice is created per card code in file name, incurred month and MBMS
card code is the C+company code in file name
invoice posting date is the date in file name
Item code in the invoice lines 4-32000-00 Fee For Service - pay comp
Check journal entry DR customer CR Fee For Service (pay comp)
check U_Footer value = 1
sales accrual journal is reversed per company code, incurred month and MBMS
journal remarks is "Reversal of Estimated sales for <company code> "
Reversal journal posting date is the date in the upload file name
Reversal journal GL accounts CR Accrued revenue DR Fee For Service (pay comp)
Reversal amount should follow the amount uploaded in SO file, not Ar
| For customer type Capitation | no invoice creation
Clinic is TPA (@AE_TPA_APCODE)
For customer type FFS (not capitation)
|  | One ar invoice is created per card code in file name, incurred month and MBMS | Fine
card code is the C+company code in file name
invoice posting date is the date in file name
|  | journal posting date is incurred month | Fine
Item code in the invoice lines CAP Patient - pay comp
Check journal entry DR customer CR CAP Patient (pay comp)
check U_Footer value = 1
sales accrual journal is reversed per company code, incurred month and MBMS
journal remarks is "Reversal of Estimated TPA Claim for <ap code>"
Reversal journal posting date is the date in the upload file name
Reversal journal GL accounts Cr AR DR TPA Income (pay comp)
Reversal amount should follow the invoice amount uploaded in SO file, not Ar
For customer type Capitation
Handled in MS007_AR (P)
Validation Check
HMDC

## AR (P)
Test Nature | Test cases | Expected | Remarks
Data | Clinic in TPA (@AE_TPA_APCODE)
For customer type Capitation
AP INVOICE UNDER AP CODE IN CONFIGURATION TABLE (@AE_TPA_APCODE) PER APCODE, INCURRED MONTH, TYPE (CAPITATION)
invoice posting date is the date in file name
Item code in the invoice lines CAP Patient - pay comp
Check journal entry CR AP DR REIMBURMENT TO PATIENT (pay comp)
cost accrual journal is reversed per ap code, incurred month and MBMS
journal remarks is "Reversal of Estimated cost for <ap code> "
Reversal journal posting date is the date in the upload file name
Reversal journal GL accounts CR REIMBURMENT TO PATIENT, DR Accrued COGS
Reversal amount should follow the amount uploaded in SO file, not Ar
For customer type not Capitation
AP INVOICE UNDER AP CODE IN CONFIGURATION TABLE (@AE_TPA_APCODE) PER APCODE, INCURRED MONTH, TYPE (CAPITATION)
invoice posting date is the date in file name
Item code in the invoice lines TPA - pay comp
Check journal entry CR AP DR TPA - Admin fee (pay comp)
cost accrual journal is reversed per ap code, incurred month and MBMS
journal remarks is "Reversal of Estimated TPA Reimbusement for <ap code>"
Reversal journal posting date is the date in the upload file name
Reversal journal GL accounts DR Accrued COGS (Panel) CR TPA INCOME (Pay comp)
Reversal amount should follow the amount uploaded in SO file, not Ar
Validation Check
HMDC

## AR
No | Test cases | Expected | Actual | Remarks | Retest 21122015 | Retest 22122015
1 | Assumption no data error: check backend UDT table has all the rows | All the content of the file should be inserted into UDT @AE_MS007_AR | Fine
| Check incurred month column in @AE_MS007_AR is last day of txn_date | If the txn_date in the file is 24102015, incurred month will be 31102015 | Fine
| check U_CostCenter and U_Insurer according to @AE_MBMS | should be able to retrieve the latest MBMS | Fine
2 | Check invoice created invoice created per company code, MBMS and incurred month | sum pay_comp by company_code, incurred_month, and U_CostCenter | Fine
| check line total | summation of pay_comp per company code, incurred month and MBMS based on AR file | Fine
| check tax group | according to default tax group set at customer master data | Fine
| check item code | as per @AE_ITEMCODE | FIne
| check journal entry posted for the invoice | as per @AE_ITEMCODE | Fine
| check U_Footer | value = 1 | Fine
| check posting date | according to the file name MS007_SO_[yyyymmdd] | Fine
| check currency | according to currency set at customer master data | Fine
3 | Check @AE_MS007_AR check U_ARInvoiceNo | as per AR invoice number created in SAP | Fine
4 | Check journal entry reversal: check journal posting date | posting date according to the file name | Failed, refer to "reversalSales". Invoice can be found in SOAccrual but no reversal created |  | Fine
| check G/L accounts posted | As per @AE_OUT_REV_GL |  |  | Fine
| check debit/credit amount | As per @AE_SOACCRUAL, use invoce to match |  |  | Fine | wrong amount, should follow "invoice" in SOAccrual. Refer to "Soreversal"
| check journal remarks | Remarks of the journal "Reversal of Estimated Sales for C1003 for Journal 1600040 " |  |  | Incomplete remarks. Refer to ReversalRemarks | Fine
5 | Check @AE_SOACCRUAL: Check U_sap_invoicedata | contains the AR Invoice number created in SAP which closes the sales order |  |  | Fine
| Check U_status | C |  |  | Fine
| Check U_RevJournalEntry | journal entry number created for the reversal |  |  | Fine
6 | Duplicate invoice: Repeat the step 1-5 with invoice number which has been closed before | throw error. Need to handle manually |  |  | Fine
7 | Sales Accrual cannot be found: Repeat the step 1-5 for an invoice which was not in SO | invoice created, not reversal journal created | Fine |  | Fine
9 | Repeat the steps 1- 5 for same company with different MBMS | two reversal journals, two invoice created
10 | Check OUT network:
| Check Cost accrual reversal: check cost journal is reversed | contains data which clinic code starts with "OUT" | Cost reversal not created even with matching invoice found in AE_COSTACCRUAL table. Refer to "ReversalCost" |  | Fine
| check journal posting date | posting date according to the file name |  |  | today's date | today's date
| check GL accounts posted | As per @AE_OUT_REV_GL |  |  | Fine
| check debit/credit amount | As per @AE_COSTACCRUAL |  |  | should be according to original invoice amount from @AE_COSTACCRUAL. Refer to "CostReversal" | wrong. Refer to costreversal2
| Check @AE_COSTACCRUAL: Check U_sap_invoicedata | contains the AP Invoice number created in SAP which closes the sales order |  |  | Fine
| Check U_status | C |  |  | Fine
| Check invoice created AP invoice created per company code, MBMS and incurred month | sum pay_comp by company_code, incurred_month, and U_CostCenter | Fine
check if invoice will be split for the same company but different MBMS
| check line total | summation of pay_comp per company code, incurred month and MBMS | Fine
| check tax group | according to default tax group set at customer master data | Fine
| check item code | as per @AE_ITEMCODE | Fine
| check journal entry posted | as per @AE_ITEMCODE | Fine
| check posting date | according to the file name | today's date |  | Fine
| check currency | according to currency set at customer master data | Fine
| Check @AE_MS007_AR check U_APInvoiceNo | as per AP invoice number created in SAP | Fine
| Check AR Invoice | Not created | Fine
| Duplicate invoice for OUT in AR file after same invoice is closed | Throw error |  |  | Data is created and journal entry is passed. Refer to "DuplicateSO" | Fine

## Sheet4
COMPANY CODE | SCHEME CODE | EFFECTIVE DATE | MBMS
1003 | G | 2015-06-01 | AXA
1003 | G | 2015-08-01 | OTHERS
IF TXN DATE IS 15/7/2015, PLEASE GET AXA
COMPANY CODE | SCHEME CODE | EFFECTIVE DATE | MBMS
1003 | G | 2015-01-01 | OTHERS
1003 | G | 2015-06-01 | AXA
IF TXN DATE IS 15/7/2015, PLEASE GET AXA
COMPANY CODE | SCHEME CODE | EFFECTIVE DATE | MBMS
1003 | G | 2015-01-01 | OTHERS
1003 | G | 2015-06-01 | AXA
1003 | G | 2015-08-01 | Bupa
IF TXN DATE IS 15/7/2015, PLEASE GET AXA

## MBMS
CREATE MBMS ENTRIES IN AE_MBMS AS PER BELOW
COMPANY CODE | SCHEME CODE | EFFECTIVE DATE | MBMS
1003 | G | 2015-06-01 | AXA
1003 | G | 2015-08-01 | OTHERS
UPLOAD FILE WITH TXN DATE IS 15/7/2015, SHOULD GET AXA
COMPANY CODE | SCHEME CODE | EFFECTIVE DATE | MBMS
1004 | G | 2015-01-01 | OTHERS
1004 | G | 2015-06-01 | AXA
UPLOAD FILE TXN DATE IS 15/7/2015, SHOULD GET AXA
COMPANY CODE | SCHEME CODE | EFFECTIVE DATE | MBMS
1005 | G | 2015-01-01 | OTHERS
1005 | G | 2015-06-01 | AXA
1005 | G | 2015-08-01 | Bupa
UPLOAD FILE TXN DATE IS 15/7/2015, SHOULD GET AXA

## Invoice_No
missing invoice number